Token Chat — Trading Module Update

In-Extension Buy/Sell via Embedded Wallet + Execution Engine

Reference product: Frontrun (frontrun.pro)

Scope addendum to brief.md / prd.md / project-development.md  ·  August 24, 2026

# 1. Summary of the Change

The extension expands from a token-scoped chat widget into a chat + trading widget. Users keep browsing GMGN, Axiom, and Padre as their chart/data UI, but buy and sell through our own execution engine and embedded wallet, directly from the injected widget. We do not modify or hijack the host site's trade buttons; we render our own trade panel and route execution through our backend.

This is a major scope expansion, not a feature toggle: it adds an embedded wallet, a transaction execution service, deposit/withdraw flows, and a per-trade fee revenue model. It also raises the security, store-review, and legal bar substantially. Chat remains the wedge and ships first (Phases 0–5 unchanged); trading follows as Phases 6–7.

# 2. Reference: Frontrun (frontrun.pro)

Frontrun has validated this exact model and is the closest comparable. Key facts observed (as of Aug 2026):

- Product: Chrome extension wallet for onchain traders — fast execution, advanced tooling, and analytics overlaid on the terminals traders already use (GMGN, Axiom, Solscan, Photon, X).

- Execution: fills powered by Turnkey key infrastructure; 0.1% flat trading fee with up to 90% cashback as the acquisition hook.

- Chains: started Solana-focused; has since added Robinhood Chain trading with cashback incentives — confirming target terminals span both chains.

- Traction/backing: claims ~50,000 users; backed by Alliance and YZi Labs.

- Trust posture: open-sourced the exact extension build shipped to the Chrome Web Store to counter wallet-extension distrust; requests broad permissions (scripting, webRequest, all-URLs hosts).

- Pattern to copy: own trade panel + hotkeys injected as an overlay; execution through their wallet and backend; host site untouched underneath.

- Our differentiator: Frontrun and peers (TradeWiz, etc.) compete on execution speed and cashback. None has a per-token social layer. Our chat rooms keyed to the CA are the wedge; trading monetizes that audience.

# 3. Trading Architecture

| Component | What it does | Key decisions |
| --- | --- | --- |
| Embedded wallet | Per-user wallet controlled via secure-enclave key infrastructure. Backend requests signatures through a policy-controlled API (per-tx caps, allowed programs, rate limits). We never hold raw keys. | Turnkey vs Privy. Self-managed key storage is prohibited (breach surface + store rejection risk). |
| Execution engine | Backend service that builds and submits transactions: aggregator routing (Jupiter on Solana), priority-fee strategy, MEV-protected submission (Jito bundles), slippage guards, blockhash/retry management, confirmation tracking. | Treated as a first-class service with reliability SLOs, multi-RPC failover, and dedicated monitoring. |
| Trade UI | Buy/sell panel in the widget: preset amounts, quick-buy hotkeys, position and PnL for the active CA. Reuses the CA-detection layer already built for chat. | Market orders only at alpha; no limit orders, sniping, or copy-trading. |
| Deposit / withdraw | Fund the bot wallet via deposit address/QR or transfer from a connected wallet; withdrawal flow back out. | Primary custody-UX and support-burden surface; deposit detection and withdrawal processing are backend tasks. |
| Fee capture | Per-trade fee ledger; optional cashback program. | Market reference: 0.1% flat + cashback. This is the revenue line for the whole product. |

# 4. Security, Review, and Legal Implications

- Widget becomes attack surface #1. The iframe now moves money. Origin-locked postMessage, strict sandbox attributes, and in-widget trade confirmation UX are mandatory. Threat model: a malicious or compromised host page attempting to induce signatures.

- Defense in depth via key policy. Per-transaction caps and allowed-program lists enforced at the key-infrastructure layer mean even a fully compromised widget cannot exceed policy.

- Chrome Web Store. A wallet extension injecting into financial sites gets maximum scrutiny — budget for longer review cycles and rejection loops in Phase 7. Consider open-sourcing the shipped extension build (Frontrun's trust approach).

- Legal. Custody / money-transmission exposure requires counsel review before trading GA. Non-custodial key-policy architecture mitigates but does not eliminate.

- Execution reliability is product risk. Dropped transactions, stale blockhashes, and RPC outages destroy trust fast. Retry/confirmation infrastructure and visible transaction status in the UI are launch requirements, not polish.

# 5. Revised Phasing

Chat phases 0–5 are unchanged and are not blocked on trading; they validate detection, injection, and distribution, all of which trading reuses.

| Phase | Scope | Estimate |
| --- | --- | --- |
| 6 — Trading Alpha | Turnkey/Privy integration (embedded wallet + signing policy), deposit flow, market buy/sell via aggregator, trade panel with presets, single chain, whitelist-only access, internal dogfooding with small real balances. | 3–5 weeks |
| 7 — Trading GA | Withdrawals, quick-buy hotkeys, position + PnL display, fee capture + accounting, Jito/MEV hardening, security review + pen test of the widget boundary, legal sign-off, Chrome Web Store re-review, open access. | 3–5 weeks |

Trading adds roughly 6–10 weeks on top of the chat MVP for the current 2-engineer team. At least one engineer on Phases 6–7 must have prior experience shipping on-chain transaction infrastructure; if neither current engineer does, plan for a third engineer or contractor on the execution engine.

# 6. Data Model Additions

| Table | Key fields |
| --- | --- |
| bot_wallets | id, identity_id, provider_wallet_id (Turnkey/Privy ref), chain, deposit_address, created_at |
| trades | id, identity_id, room_id (CA), side, amount_in, amount_out, tx_signature, status (pending/confirmed/failed), fee_amount, created_at, confirmed_at |
| deposits / withdrawals | id, identity_id, amount, tx_signature, status, created_at |
| fee_ledger | id, trade_id, fee_amount, cashback_amount, created_at |

# 7. Open Decisions (Blocking for Phase 6)

- Launch chain — BLOCKING. Execution code is entirely chain-specific. The brief says Solana; the PRD/dev plan say Robinhood Chain. Frontrun supports both, so the target terminals may span both — decide the launch chain (or a sequence) before any execution work begins.

- Key infrastructure vendor: Turnkey vs Privy — evaluate on cost, chain support depth, and policy-engine flexibility.

- Fee structure: bps per trade; cashback yes/no and its funding source.

- Alpha scope: market orders only (recommended) vs limit orders at launch.

- Address normalization fix: room IDs must be chain-aware — Solana base58 addresses are case-sensitive and must not be lowercased; lowercase-normalize only EVM-style addresses.

# 8. Strategic Framing

We are entering a space where Frontrun (VC-backed, ~50k users) and others already compete on execution speed and cashback economics. We should not try to win on those axes at launch. The chat layer — one shared room per token, reachable from any terminal or the web — is the differentiator no pure trading extension has. Keep chat as the wedge; treat trading as the monetization of that audience, not the other way around.